## Standard
| Project Implementation Process (PIP) Stage | PIP Reference | Funder (Lead Agency) | End user | Purchaser (DPTI) | Provider (planning study /construction team) | Project Director | DPTI Project Risk Manager | Project Manager | Cost Manager | Lead PSC | disciplines | Project Director (Lead Agency Representative) | DPTI Project Risk Manager (Infrastructure Agency Representative) | Project Manager | Cost Manager | Lead Professional Service Contractor (Architecture or Engineering) or Coordinating Architect/Engineer | Discipline PSC or Lead PSC Subcontractor
GOVERNMENT STRATEGIES AND KEY DIRECTIONS |  |  | R | [9 empty] | DPTI = Department of Planning, Transport and Infrastructure, PCG = Project Control Group
IDEAS TO MEET NEEDS |  |  | R | I | I | [7 empty] | R = Responsibility, I = Input
CORPORATE PLANNING PHASE |  |  | R | I | I | [7 empty] | CAD = Computer Aided Drafting
| Determine broad Lead Agency parameters for project program, budget and quality |  | R | I | I |  | R | [5 empty] | Manage that there is approval by the Lead Agency delegate of the initial scope and associated budget, program and quality standards | Assist the Lead Agency to determine initial parameters by providing DPTI building industry data, knowledge and lessons learned.
PLANNING STUDY |  | 5.1
| Establish project control group and other organisation structures |  | I | I | R | [7 empty] | Determine who will represent Lead Agency interests on the Project Control Group | Assist the Lead Agency to establish the project organisation structure by providing organisation models. Establish Project Control Group
| Project Team management and coordination |  |  |  | I | R | I | I | R | I | I | I |  | Manage that the there is implementation of effective team coordination | Implement effective team briefings and coordination | Implement agreements on planning study team coordination | Implement agreements on planning study team coordination | Implement agreements on planning study team coordination
| Establish team briefing, communication and reporting |  |  |  | R | I | I | I | R | I | I | I | Provide detailed DPTI and professional service contractor briefings | Manage that there is implementation of briefing, and communication and reporting systems in accordance with DPTI policies | Implement effective briefing, communication and reporting systems in accordance with DPTI policies | Attend plannig study team briefings and implement agreements on team communication and reporting | Attend planning study team briefings and implement agreements on team communication and reporting | Attend planning study team briefings and implement agreements on team communication and reporting
| Project Control Group |  | I | I | R | I | I | R | I | I | I | I | Attend regular Project Control Group meetings | Chair and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings | Attend and report to regular Project Control Group meetings
| Planning Study Team |  | I | I | I | R | I | I | I | I | R | I | Attend planning study team meetings as relevant. | Attend planning study team meetings as relevant. | Attend regular planning study team meetings. | Attend regular planning study team meetings. | Chair and minute regular planning study team meetings. | Attend regular planning study team meetings.
| Undertake planning study |  | I | I | I | R | I | I | I | I | R | I | Coordinate the input of Lead Agency and End User representatives into the planning study process. | Facilitate the planning study process by ensuring input of DPTI relevant standards, guide notes, lessons learned and clarifying any project management issues. | Manage the planning study process by coordinating the professional service contractor services to achieve an endorsed planning study and report clearly defining all scope, cost, program, risk, quality and procurement aspects. | Work with the Lead PSC and other disciplines to prepare and document cost estimates of the planning study and staging for inclusion with the Contract Material. Advise the PCG as required in regard to the planning study. development process. | Develop the detailed planning study incorporating preferred planning study option to form the basis of costing of the planning study and formulation of project staging recommendations. Liaise with the Project Manager and the PCG in achieving endorsement of the planning study. | Work with the Lead PSC and End Users to develop the full planning study statement inclusive of project staging, site service strategies, earthquake strategies etc. Liaise with the disciplines, Project Manager and the PCG in achieving endorsement of the planning study.
| Clarify the functional objectives of the project. |  | R | I | I | I | R | I | I | I | I | I | Manage that the project objectives are sufficiently clear to form the basis of the consultant's work. | Manage that the project objectives are clearly stated in the project and professional service contractors briefs. | Coordinate that the project objectives are understood and implemented by the planning study team. | Incorporate into the cost plan any costs arising out of project functional objectives. | Incorporate into the planning study options the project functional objectives. | Incorporate into the planning study options the project functional objectives.
| Identify statutory, planning and environmental issues |  |  |  | I | R | I | I | I | I | R | I | Input as relevant into the achievement of statutory, planning and environmental approvals | Input as relevant into the achievement of statutory, planning and environmental approvals | Facilitate the achievement of statutory, planning and environmental approvals | Incorporate into the cost plan any cost issues arising out of statutory, planning or environmental approvals | Provide advice from all relevant parties, agree timing and scope of approvals with DPTI and achieve statutory, planning and environmental approvals. | Provide advice and assist in the achievement of approvals.
| Identify cultural and heritage issues |  | R | I | I | I | R | I | I | I | R | I | Ensure that the brief of requirements identifies any known cultural or heritage issues. | Contribute to the definition of heritage issues through the use of DPTI historic buildings asset information. | Facilitate the achievement of any cultural or heritage approvals. | Incorporate into the cost plan any costs arising out of cultural or heritage issues. | Provide advice from all relevant parties, agree timing and scope of any approvals with DPTI and achieve relevant heritage or cultural approvals. | Provide advice and assist in the achievement of approvals.
| Define key operational parameters and functional relationships |  | R | I | I | I | R | I | I |  | I | I | Manage that the key operational and functional relationships are sufficiently clear and properly endorsed by the End Users, PCG and the SC to form the basis of the planning study team's work. | Manage that parameters and relationships are formally defined by the Lead Agency and responded to by the Lead PSC and disciplines. | Coordinate the work of the planning study team to meet the defined project parameters. | Prepare a cost plan to the defined parameters. Advise of any outstanding information immediately it is evident. | Define parameters and functional relationships and manage that they are the basis for the disciplines' work. | Planning study to the defined parameters and functional relationships. Advise of any outstanding information immediately it is evident.
| Contingencies |  | I | I | R | I | I | R | I | I | I | I |  | Manage that there is assessment and determination on appropriate design and construction contingency allowances on the basis of risk analysis. | Contribute to assessment of required design and construction contingency allowances. | Contribute to assessment of required design and construction contingency allowances. | Contribute to assessment of required design and construction contingency allowances. | Contribute to assessment of required design and construction contingency allowances.
| Prepare order of cost estimate |  | I | I | I | R | I | I | I | R | I | I | Make available detailed brief and any background information to inform on project cost | Manage that DPTI information on existing buildings and on rates/market etc is researched and reviewed and is incorporated into the order of cost estimate prepared. | Coordinate the work of the planning study team to prepare the estimate. | Prepare order of cost estimate to complete project based on brief and historical data | Assist in the preparation of the order of cost estimate by providing planning study detail sufficient to prepare an order of cost estimate. | Input into the order of cost estimate.
| Identify Government, DPTI and Lead Agency policies and codes relevant to the project. Refer to the Project Implementation Process and the Government Buildings Energy Strategy |  | R |  | R |  | R | R | I | I | I | I | Make available all relevant policies and codes to the project team. | Manage that information on policies and codes is available to the project team for review. | Manage that information on policies and codes is incorporated into project team proposals. | Review requirements of policies and codes to understand and incorporate the potential cost impact. | Review requirements of policies and codes to manage that the requirements are understood, incorporated into the planning study proposals and documented. | Review requirements of policies and codes to manage that the requirements are understood, incorporated into the planning study proposals and documented.
| Undertake Risk Analysis |  | I | I | R | I | I | R | I | I | I | I | Manage that the PCG reviews the professional service contractors/DPTI risk analysis and advises the SC. | Prepare DPTI Risk Management system report on risk profile. | Work with DPTI to provide a comprehensive appraisal of project risks | Work with DPTI to provide a comprehensive appraisal of project risks | Work with DPTI to provide a comprehensive appraisal of project risks | Work with DPTI to provide a comprehensive appraisal of project risks
| Consider ESD issues in the brief and planning study |  | R | I | I | R | R | I | I | I | R | I | Determine the response to Government ESD policy that will apply to the project | Manage that the requirements of the Government Buildings Energy Strategy are implemented | Coordinate that the ESD policy and brief requirements are met by the planning study team. | Cost the detailed requirements of ESD policy and brief requirements into cost plans and estimates | Meet the detailed requirements of the briefed ESD initiatives | Meet the detailed requirements of the briefed ESD initiatives
| Identify existing building issues |  | I | I | I | R | I | I | I | I | R | I | Make available all appropriate information and assist in site survey processes. Organise End User staff input as appropriate to facilitate clear understanding by the professional service contractors. | Manage that DPTI information on existing buildings is researched, reviewed and forms part of planning study team proposals. | Coordinate that existing information is incorporated into planning study proposals. | Review information on existing buildings to understand and incorporate the potential cost impact. | Review existing audit reports and surveys of site buildings and environs to manage that the physical condition and status of code compliance is understood, documented and taken into consideration in proposals. | Review existing audit reports and surveys of site buildings and environs to manage that the physical condition and status of code compliance is understood, documented and taken into consideration in proposals.
| Prepare indicative program |  | I |  | I | R | I | I | R | I | I |  | Input into indicative program by identifying critical milestones or required staging | Manage that there is assessment and determination on appropriate timeframes for key activities. | Prepare indicative program including milestones, staging and time contingency allowances. | Contribute to preparation of indicative program. | Contribute to preparation of indicative program. | Contribute to preparation of indicative program.
| Identify all reasonable service delivery options (including a "no-build" option) |  | R | I | I | I | R | I | I | I | I | I | Manage the assessment of options so that all appropriate options to meet agreed service needs are considered. Manage that the report is endorsed by all key stakeholders and the SC | Coordinate that there is preparation of a planning study that identifies service delivery options. Manage that the report is endorsed by the PCG | Manage that there is preparation of a planning study that identifies service delivery options | Prepare the planning study cost plan and estimates to reflect service delivery options | Prepare the planning study coordinating and arranging all input from the discipline psc's, Cost Manager and Project Manager. | Input to the planning study as required providing all necessary engineering advice and Contract Material.
| DELIVERABLES | 5.1
| Planning Study Review |  | I | I | R | I | I | R | I | I | I | I | Participate in DPTI planning study review at 90% completion of planning study | Manage and implement the DPTI planning study review at 90% completion of planning study with Lead Agency, End Users and planning study team. | Participate in DPTI planning study review at 90% completion of planning study | Participate in the planning study review at 90% completion of planning study and manage that any issues identified are resolved in the planning study proposals. | Participate in the planning study review at 90% completion of planning study and manage that any issues identified are resolved in the planning study proposals. | Participate in the planning study review at 90% completion of planning study and manage that any issues identified are resolved in the planning study proposals.
| Prepare final Cost estimate | [12 empty] | Manage that there is DPTI input into the estimate through budget risk advice. | Coordinate the work of the planning study team to prepare the estimate. | Prepare planning study cost estimate | Assist in the preparation of the planning study cost estimate by providing sufficient planning study detail. | Input into the planning study cost estimate
| Prepare the final planning study report. |  | I | I | I | R | I | I | I | I | R | I | Submit final planning study report to the SC | Manage that there is preparation by the planning study team of the final planning study. | Coordinate the preparation by the planning study team of the planning study Contract Material. | Contribute to the preparation of the final planning study report | Prepare the final planning study report | Contribute to the preparation of the final planning study report